## 20 Development Goals
Order | Phase | Goal | Objective | Reviewable Deliverable | Completion Criteria | Depends On (Goal #) | Suggested Owner | Technology / Spec | Status | Progress as of 2026-09-27 | Remaining work / next action | Evidence
1 | Incubation | Define the product and pilot audience | Define the Android photo pilot for journalists and field documenters sharing originals with reviewers. | Pilot brief with user journeys, success metrics, and claim vocabulary. | Approve examples distinguishing record recovery, exact integrity, and capture checks; exclude scene-truth claims. | None | Product lead | Product contract; separate claims | Complete | Product brief and pilot audience documented. | Planning complete; implementation tracked below. | docs/01-product-brief.md
2 | Incubation | Freeze pilot scope and free-development constraints | Limit the first milestone to Android JPEG capture, local verification, offline queueing, and signed record lookup. | Scope, available-hardware plan, free-tooling constraints, and deferred-feature list. | Define Android support and reference tiers; assign accountability; use existing or freely borrowed devices and no paid services; defer production iOS, video, editing, and browser UI; permit the separate iPhone feasibility experiment. | 1 | Armaan Singh (accountable); Codex (documentation) | Supported first release; staged Android pilot | Complete | Android pilot scope and free-only development constraints documented. iPhone research experiment subsequently authorized. | Production iOS remains deferred; no paid services or hardware purchases. | docs/02-pilot-scope-and-free-development.md
3 | Discovery | Define threat model and privacy policy | Specify attacker capabilities, public/private data boundaries, enrollment policy, and assurance outcomes. | Threat model, data map, retention/deletion policy, and assurance decision table. | Define offline, expired-challenge, unsupported-attestation, and failed-validation behavior; no media uploads or public identity/location by default. | 1, 2 | Armaan Singh (accountable); Codex (policy documentation) | SEC1–6; PR1–4 | Complete | Threat model, privacy rules and assurance outcomes documented. | Security controls still require implementation and validation. | docs/03-threat-model-and-privacy-policy.md
4 | Discovery | Design capture and verification experiences | Map capture, processing, pending registration, sharing, verification, deletion, and recovery. | Reviewable screens and state-transition diagrams. | Cover permission denial, no connection, storage failure, and missing records; distinguish registration state from sharing state. | 1, 3 | Armaan Singh (accountable); Codex (design/prototype) | CAP; OPS3–4; independent result rows | Complete | Capture/verification screens, states and clickable prototype delivered. | Prototype behavior is simulated; production implementation pending. | docs/04-capture-and-verification-design.md
5 | Feasibility | Prepare benchmark data and test harness | Create separate tuning and frozen evaluation data for photo watermark and integrity experiments. | Versioned transformation harness, licensed corpus inventory, and reproducible reports. | Prepare at least 1,000 held-out photos and 300,000 unmarked inputs for final evaluation; include actual screenshots and source-disjoint data. | 2, 3 | Armaan Singh (accountable); Codex (harness/acquisition) | QA1–4; photo subset only | In progress | Harness, 11,200 distinct source images, 53 resolution variants and 300,000-case stress recipe plan prepared; tuning review recorded. | Rights/content/near-duplicate review, final evaluation eligibility and real screenshots pending. Stress recipes are not completed evaluations. | docs/05-benchmark-data-and-harness.md
6 | Feasibility | Benchmark conventional invisible watermarks | Test non-ML transform-domain candidates for payload capacity, recovery, quality, and Android cost. | Pinned candidate comparison with payload layout and license review. | Measure complete-ID recovery after screenshots, crops, and sharing transforms; report coding overhead, artifacts, false positives, and latency. | 5 | Armaan Singh (accountable); Codex (research implementation) | WM1–5, WM7; conventional baseline first | Blocked | Desktop study and Android research APK delivered. iPhone v3 default implemented: 125/125 marked simulations, 0/100 noise detections; all six previous v2 misses recovered. Linux regression and v3 AddressSanitizer checks pass. | No Android phone available. Run Mac validation, Apple codec tests and iPhone 16 Pro screenshot/performance/visual checks. V3 host median 4.392 s; no production qualification. | ios-benchmark/ADAPTIVE-V3.md
7 | Feasibility gate | Select watermark approach and support envelope | Choose conventional watermarking if it meets the envelope; benchmark learned candidates only if needed. | Architecture decision with usable capacity, runtime, license, supported transformations, and measured tradeoffs. | Fit 128-bit ID plus routing/coding or explicitly document a capacity redesign; complete feasibility on available physical devices, list untested tiers, and restrict support claims accordingly. | 6 | Engineering + product + security leads | WM1–8; optional PyTorch/ONNX/LiteRT | Not started | V3 selected only as iPhone research default; v1/v2 preserved. No production watermark or support envelope approved. | Complete physical-device feasibility and quality gates before production selection. | ios-benchmark/TESTING.md
8 | Foundation | Set up repository, Android app, and CI | Create a reproducible native Android project with secure development practices. | Kotlin/Compose app shell, build pipeline, dependency locks, signing configuration, and environment separation. | CI builds an installable development APK and runs relevant checks; secrets stay outside source; production trust rejects development certificates. | 2, 7 | Android + platform engineers | Kotlin; Jetpack Compose; Gradle; CI | Not started | Repository and separate Android/iPhone research projects exist. Production Android foundation and CI goal not yet started. | Proceed after goal 7; research APK/Xcode project does not satisfy production completion criteria. | README.md
9 | Foundation | Specify records and deterministic integrity rules | Freeze JPEG canonicalization, request encoding, certificate format, receipt format, and protocol versions. | Schemas, trust policy, golden fixtures, and interoperable signed test vectors. | Agree on SHA-256 file/pixel hashes, pinned decoder behavior, domain separation, idempotency, expiry, revocation, and deletion tombstones. | 3, 7 | Protocol + security engineers | Rust shared core; COSE/ES256; INT1–2; CAP4–7 | Not started | No production implementation completed for this goal. | Await listed prerequisites; research tests do not satisfy this release goal.
10 | Implementation | Build native photo capture | Implement in-app JPEG capture with permission handling, normalized orientation/color, and protected temporary storage. | CameraX capture flow and immutable export storage foundation. | Capture works on all reference devices; denied permissions and low storage are handled; gallery imports cannot earn app-capture claims. | 4, 8, 9 | Android engineer | CameraX; Kotlin; PR1; CAP3 | Not started | No production implementation completed for this goal. | Await listed prerequisites; research tests do not satisfy this release goal.
11 | Implementation | Integrate watermarking and final export hashes | Embed before final encoding and compute hashes over the stored final export. | Android watermark pipeline and Rust integrity bindings. | Reopen and verify exports; canonical hashes agree with golden fixtures; visible quality and performance are measured on reference phones. | 7, 9, 10 | Android + watermark + protocol engineers | Selected watermark runtime; Rust/JNI; CAP3–4 | Not started | No production implementation completed for this goal. | Await listed prerequisites; research tests do not satisfy this release goal.
12 | Implementation | Implement device enrollment and capture challenges | Enroll installation keys and obtain session-bound one-use challenges for online captures. | Android Keystore integration, enrollment validation, and challenge API. | Server validates available Play Integrity/key-attestation evidence and request binding; invalid enrollment, replay, and expired challenges follow policy. | 3, 8, 9 | Android + backend + security engineers | Android Keystore; Play Integrity; CAP1–2; SEC1–2 | Not started | No production implementation completed for this goal. | Await listed prerequisites; research tests do not satisfy this release goal.
13 | Implementation | Build transactional registration and certificate issuance | Accept locally signed requests, validate evidence, and durably issue public certificates. | Registration service, immutable records, protected server signing, and idempotent retries; development trust kept separate. | Consume challenge atomically with record creation; identical retries return the same result; conflicting IDs/requests fail; success follows durable commit. | 9, 12 | Backend engineer | Rust/Axum; PostgreSQL; free/local signing prototype; trusted public signing remains gated by CAP7 and SEC3. | Not started | No production implementation completed for this goal. | Await listed prerequisites; research tests do not satisfy this release goal.
14 | Implementation | Add offline queueing and safe sharing | Persist capture work and reconcile registrations after crashes, outages, and app restarts. | Durable local state machine, bounded retries, receipts, progress/cancel UI, and share-sheet integration. | Share only checked, locally signed immutable exports; label pending registration; offline/expired sessions never receive fresh-challenge claims; no unexplained media loss. | 11, 12, 13 | Android engineer | Room; WorkManager; Android Sharesheet; OPS3–4 | Not started | No production implementation completed for this goal. | Await listed prerequisites; research tests do not satisfy this release goal.
15 | Implementation | Build independent Android verification | Extract IDs and hash imported media locally, then verify signed records against the trust policy. | Verifier flow, lookup API, bounded screenshot region selection, and approved exact-digest fallback. | Display signature, issuer, content, capture checks, and availability separately; copied watermark cannot earn integrity success; no default media upload. | 9, 11, 13 | Android + backend + protocol engineers | Rust verification core; WM5, WM7–8; SEC4–6; PR3 | Not started | No production implementation completed for this goal. | Await listed prerequisites; research tests do not satisfy this release goal.
16 | Implementation | Implement record management and recovery | Allow local deletion, authorized public removal, receipt export/import, and accountless management recovery. | Deletion APIs/UI, recovery credential flow, private tombstones, and receipt portability. | Unauthorized deletion fails; removed IDs never reappear after restore; copied receipts remain signature-checkable subject to trust status; explain credential-loss consequences. | 3, 13, 14, 15 | Android + backend engineers | PR4; OPS2; private recovery credentials | Not started | No production implementation completed for this goal. | Await listed prerequisites; research tests do not satisfy this release goal.
17 | Production readiness | Harden backend operations and app distribution | Prepare isolated production services, trust-key rotation, signed model delivery if used, monitoring, and restore procedures. | Infrastructure as code, dashboards, rate limits, retention jobs, incident/runbook documentation, and production signing setup. | Demonstrate restore and deletion preservation; measure lookup targets; verify historical keys, revocations, cache age, and model-update signatures where applicable. | 13, 15, 16 | Platform + security engineers | Existing infrastructure or verified no-cost hosting; local prototype otherwise; SEC4–5; OPS1–5. | Not started | No production implementation completed for this goal. | Await listed prerequisites; research tests do not satisfy this release goal.
18 | Validation | Run release-candidate quality and security gates | Evaluate the frozen build across reference phones, transforms, adversarial inputs, and interruption scenarios. | Per-device benchmark report, privacy traffic audit, parser/fuzz results, and resolved release-blocker list. | Zero false exact-integrity results in release corpus; meet declared recovery/quality gates; report confidence bounds; no replay acceptance, leakage, canonical mismatch, or unexplained loss. | 5, 14, 15, 16, 17 | QA + security + engineering leads | QA1–5; photo p95 goal ≤2 s; incremental memory goal <512 MB | Not started | No production implementation completed for this goal. | Await listed prerequisites; research tests do not satisfy this release goal.
19 | Pilot | Run a closed Android pilot and approve release | Distribute to a small reviewer cohort and validate comprehension, reliability, and the supported-device envelope. | Pilot findings, fixes, final support matrix, privacy disclosures, store assets, and signed release checklist. | At least 9/10 reviewers distinguish recovery from integrity; critical issues resolved; rerun affected checks; document direct-APK distribution and available attestation evidence. | 18 | Product + QA + release leads | Direct signed-APK closed pilot; delivery step 6 | Not started | No production implementation completed for this goal. | Await listed prerequisites; research tests do not satisfy this release goal.
20 | Deployment | Deploy and monitor the Android photo pilot | Release production backend and staged Android distribution with rollback and support coverage. | Versioned production release, smoke-test evidence, alert ownership, support process, and follow-up backlog. | Capture → registration → independent verification succeeds in production; alerts and rollback are exercised; publish measured limitations and monitor staged rollout before expansion. | 19 | Release + platform + product leads | Direct signed-APK staged rollout; no-cost hosting if compliant; production monitoring. | Not started | No production implementation completed for this goal. | Await listed prerequisites; research tests do not satisfy this release goal.
Note on J2: Step 1 documented in docs/01-product-brief.md. Working product decisions established under the instruction to proceed; external validation and implementation remain pending.
Note on J3: Planning complete; supersedes the paid feasibility proposal. Use existing/free resources only. Actual device inventory and measurements remain pending. See docs/02-pilot-scope-and-free-development.md.
Note on J4: Policy baseline complete: threat register T01–T14, assurance matrix, data map, retention/removal, and release gates. Implementation and independent review pending.
Note on J5: Screen specification, lifecycle diagrams, failure-state copy, and local interactive prototype delivered. Syntax and 33 prototype logic assertions passed. Browser visual review, user testing, and Android implementation remain pending.
Note on J6: 100 tuning images visually screened by Codex; this is not rights or release approval. See benchmark/reviews/tuning-visual-v1.json. 34 automated tests pass.
Note on J7: Desktop study complete: 3,668 scheduled cases on 92 positive and 1,000 negative candidates, plus 45 native-resolution variant cases. One positive/six negative ICC failures retained. Android research APK built and host core tests pass. User confirmed no phone on 2026-09-26. Actual screenshots, native latency/peak memory and display artifact checks are unmeasured; no production candidate selected.

## Scope and Decisions
Topic | Working decision
Purpose | 20 development goals for the Android photo pilot, with progress recorded as of 2026-09-27. Research evidence does not imply production readiness.
Source | ProofCam_Product_Spec.docx, Draft v0.4, September 25 2026, plus the product decisions discussed in this conversation.
Initial scope | Native Android JPEG capture and verification, invisible identifier, exact integrity checks, server-signed records, offline registration queue, safe sharing, and deletion/recovery.
Deferred scope | Production iPhone app, video/audio, partial-interval verification, browser verification, editing and manufacturer sensor-origin assurance remain deferred. A separate iPhone research app is now implemented for feasibility testing.
Watermark choice | Conventional watermarking first; no AI required for current research. iOS adaptive v3 is the research default, with v1/v2 selectable. Production selection awaits device, quality and support-envelope gates.
Technology status | Android pilot floor: Android 14/API 34, arm64-v8a. Illustrative comparison targets, not required purchases: Galaxy A15 5G 4/128 GB, Pixel 8a 8/128 GB, Galaxy S24 US 8/128 GB. Kotlin/Compose/CameraX and Rust remain working technology choices; watermark runtime and protocol details await later gates.
Sharing policy | Sharing can occur after final export validation and local signing, before registration. Pending registration is explicit and the registration queue continues independently.
Assurance policy | Offline or expired-challenge capture receives no fresh online challenge claim. Unsupported attestation may receive basic integrity certification under policy; failed security validation is not silently downgraded into trusted capture.
Ownership | Armaan Singh is accountable; Codex assists with documentation and implementation when tasked. Independent security reviewer remains to be appointed. See docs/02-pilot-scope-and-free-development.md. Free resources only; no release date.
Dependencies | Numbers refer to roadmap goals. Listed dependencies are prerequisites; goals may overlap once prerequisites are satisfied.
Release gates | Apply photo-relevant spec gates to the pilot. Any narrowed support envelope must be explicitly approved and published. Integrity correctness and privacy requirements remain blocking.
Tracking | Goals 1–4 complete as planning/design deliverables. Goal 5 in progress. Goal 6 host research implemented through iOS v3; Android device validation blocked and Mac/iPhone validation pending. Goals 7–20 remain not started as production goals; preparatory repository/research-app work is recorded separately.
Deployment readiness | Check then-current platform, SDK, attestation, and Google Play policies during implementation and before release. This workbook is not a current-policy audit.
Free-development constraint | Existing or freely borrowed devices; local compute; free tools and licensed data; no paid services or store enrollment. Direct signed APK distribution. Public hosting/signing remains gated on compliant no-cost resources; never claim unavailable attestation.
Available iPhone | User reports iPhone 16 Pro and current Xcode on their Mac. Mac validation and physical-device tests have not been run here. No Android phone is available.
Latest implementation | dd40e45: adaptive iPhone v3, committed and pushed. Smaller repeated tiles, soft error correction, adaptive embedding and expanded geometric search.
Next action | On the Mac: pull latest code and run bash ios-benchmark/tools/validate-mac.sh. Then collect real iPhone screenshots, visual review and performance results. Android physical validation remains separately blocked.

## Research Progress
Workstream / check | Current result | Status / limitation | Evidence
Snapshot | Updated 2026-09-27; implementation dd40e45. | Free-only development. Research app, not production release. | README.md
iPhone app | SwiftUI/Xcode project prepared; adaptive v3 default; v1/v2 selectable. | Apple SDK build, signing, simulator and device execution pending. | ios-benchmark/README.md
V3 geometric simulation | 125/125 marked cases recovered: 25 transforms on five sources. Includes resizes, crops, rotations, mirrors, JPEG and synthetic viewer chrome. | Three development sources plus two preselected additional photos; not broad release qualification. | benchmark/reports/step06-ios-adaptive-simulation.json
Previous failures | Original three sources: v2 69/75 → v3 75/75. Two additional photos: 50/50. | All six previous v2 misses fixed in this simulation; arbitrary combinations not guaranteed. | benchmark/reports/step06-ios-adaptive-comparison.json
Negative simulation | No detections on 100 unmarked procedural noise inputs; no unexpected IDs in all 225 cases. | Not a natural-photo false-positive study or cryptographic validation. | benchmark/reports/step06-ios-adaptive-simulation.json
Linux Release regression | 34 discovered: 30 passed, four optional tests skipped; zero failures. Simulation executed separately. | Skipped: two fixture generators, optional diagnostic, separately run simulation. | benchmark/reports/step06-ios-adaptive-validation.json
AddressSanitizer | Five active v3 tests passed; two optional tests skipped; no errors. | Leak detection disabled; not full simulation or Apple code coverage. | benchmark/reports/step06-ios-adaptive-validation.json
Project checks | App Swift syntax parse and deterministic Xcode project generation passed. | Not Apple SDK typechecking or Xcode build evidence. | benchmark/reports/step06-ios-adaptive-validation.json
Image quality | Photo SSIM v2→v3: 0.941→0.958; 0.912→0.950; 0.947→0.962. | PSNR not uniformly improved; procedural noise quality worsened. Invisibility and Apple JPEG quality not qualified. | benchmark/reports/step06-ios-adaptive-comparison.json
Host recovery time | Median 4.392 s; p95 6.903 s; maximum 8.953 s across 225 cases. | Slower than v2; not iPhone timing or a mobile latency pass. | benchmark/reports/step06-ios-adaptive-comparison.json
Apple codec checks | Six Apple-only tests prepared. | Not executed; run Mac validation script. | ios-benchmark/tools/validate-mac.sh
Physical iPhone evidence | iPhone 16 Pro available to user. | Pending Mac build and actual screenshots, display review, latency and memory measurements. | ios-benchmark/TESTING.md
Physical Android evidence | Research APK built; no Android phone available. | Blocked; iOS results do not qualify Android. | docs/06-conventional-watermark-final-report.md
Production gate | No production candidate selected; deployment not started. | Goals 5/6 remain incomplete; goals 7–20 remain open. | docs/06-conventional-watermark-final-report.md